## Cover Sheet
UN3502 - Known Error Log
Version K2.98 (02/10/2024)
Classification: NHS Restricted
Contents
1. Known Errors
2. Known Errors (with Workarounds)
3. Known Errors - Data Warehouse
4. Closed Since Last Issue
5. Closed Consolidated

## Known Errors
Classification Description | Service Desk Summary | Workaround Indicator | Problem Number | Month Raised | Release | New Addition
Absence \ Shared Parental Leave | When an employee is in receipt of both OSHP and SSHP and the combined amount exceeds their Normal Full pay amount, the payment of OSHP is not being reduced accordingly. | Y | PRB2002824 | 2024-08-12 14:13 | 63.0.0.0
Absence \ Sickness | Periods of Work Related sickness absence are being incorrectly deducted from an employee's OSP entitlement when a previous absence starts before and ends after the 365th day prior to the current sickness absence start date. |  | PRB2002815 | 2024-07-31 15:09 | 63.0.0.0
Access Security \ BI | When using the ‘Create New Data Model’ feature in BI Publisher, users are presented with folders for all Organisations IDs. Users cannot use or open folders associated to Organisations for which they are not part but the folders are visible. |  | PRB2002790 | 2024-06-28 08:58
HR \ Assignment Mass Update | The Mass Update of Employee Assignments updates the assignment costing information in 'CORRECTION' mode when ‘UPDATE' mode is selected, ignoring the effective date set by the user. |  | PRB2002740 | 2024-04-30 10:07
HR \ Competencies | Competences that are removed at Position Level are removed from Business Group Level if Set |  | SR1057935 | 2013-01-08 14:33 | 63.0.0.0
HR \ IAT | The Automated IAT Person Matching form is not sorting the most current employee records first as per the defined priority. |  | PRB2002812 | 2024-07-30 09:42 | 63.0.0.0
HR \ IAT | When National Competences are being updated with pre-existing details, this triggers a new update sending a notification for every run of NHS Multiple Employer Competence Update Process for the same person competence. |  | PRB2002818 | 2024-08-06 11:47
HR \ Terminations | When an employee with multiple assignments is terminated the Exit Questionnaire will not be sent to any assignment if the 'Exit Questionnaire Required' field is set to 'No' for the Primary Assignment, even where the non-primary assignments are set to 'Yes'. |  | PRB2002686 | 2023-12-20 16:36 | 63.2.0.0
Interfaces | When large E-Recruitment Interface files are loaded, Applicants can incorrectly be flagged as an existing Applicant.Employee. |  | PRB2002849 | 2024-09-20 15:21 |  | Y
Learning Management | Administrators are unable to create external learning records using the Search and View Learner page for employees or applicants who do not have a supervisor. |  | PRB2002835 | 2024-08-29 16:02 | 62.3.0.0
Learning Management | Learners are incorrectly able to withdraw from a class within the time defined in the 'Withdrawal Restriction Period' field. |  | PRB2002843 | 2024-09-09 14:14
Learning Management | When a Manager enrols a Learner onto a class of Offering type, "Online e-Learning" that requires approval, the following message is incorrectly displayed. ""Your request to enrol in the class XXXXXX has been submitted for manager approval | Y | PRB2002844 | 2024-09-10 13:52
Learning Management \ Catalogue \ Class | When a learner is enrolled onto a class (status 'Confirmed') and has a subsequent status update (e.g Withdrawn), and then the learner is then reenrolled with a status of 'Waitlisted', no notification is sent to the learner. |  | PRB2002776 | 2024-06-10 12:09 | 63.0.0.0
Learning Management \ Catalogue \ Class | When a Learning administrator changes a Learning Enrolment status via the enrolment popup window, the following error can be displayed 'Error: ORA-00001: unique constraint...'. |  | PRB2002827 | 2024-08-16 10:55 | 62.3.0.0
Learning Management \ Class Administration | When using the Class Scheduler - Specific Dates option, not all the class attributes are copied to the new class |  | PRB2002842 | 2024-09-05 16:37 | 62.3.0.0
Learning Management \ Competencies | Overlapping Competencies on an existing competence throws up an error message which is blank, therefore doesn't advise the user what the issue is |  | PRB2002219 | 2022-01-21 10:33
Learning Management \ Competencies | Within the Learner Homepage in the My Current Certifications table, expired Certifications are being incorrectly displayed as Certified. |  | PRB2002771 | 2024-06-06 11:55
Learning Management \ Content \ Play | Learning Administrators cannot update a Learning Object when the number of rows exceeds 301 and the Learning Object they are searching for is listed after the first 301 rows. |  | PRB2002833 | 2024-08-27 14:55
Learning Management \ Enrolment | The Learning Certification course enrolment page uses a different user interface to the course enrolment page. |  | PRB2002807 | 2024-07-17 15:29
Learning Management \ Enrolment | Within the Learner Homepage, the date in the Class Information section under 'You Completed the class' is different to the completion date in the Content Outline section. |  | PRB2002822 | 2024-08-08 14:07
Learning Management \ Learner Groups | When creating a Learner Group using an Eligibility Profile. The process, 'Eligibility Profiles for Learner Groups' will fail where person level items have been referenced in the assignment set, these are items beginning &PER. |  | PRB2002685 | 2023-12-18 16:33
Notifications \ Appraisals | The "Pass Through Gateway Score" entered in a self service appraisal does not transfer to the Appraisal and Development Summary EIT |  | PRB2002845 | 2024-09-10 15:24
Notifications \ HR | When a User accesses a notification from a sorted Worklist and selects the 'Display Next Notification after my Response', the latest notification is displayed instead of the next Notification. |  | PRB2002737 | 2024-04-29 13:58
Notifications \ Learning Management | When managers are sent email approval notifications, there is no message to indicate that the approval/rejection comments must be recorded within the quotation marks. |  | PRB2002785 | 2024-06-25 12:16
Notifications \ Self-Service | Self Service Users can on rare occasions be able to view Employee Names on notifications in their worklist which do not relate to the notification request details. |  | PRB2002558 | 2023-05-30 15:14
Notifications \ Self-Service | For any absences created via a mobile device, the following error message is received when a supervisior returns the absence for correction. "An invalid setup has been detected for the current transaction type in approvals management. Please contact your system administrator." |  | PRB2002674 | 2023-11-27 09:37
Notifications \ Self-Service | When a Learning Administrator changes the enrollment status from 'Confirmed' to 'Did not Attend (DNA)', the notification sent to the learner does not specify the Enrolment status. |  | PRB2002836 | 2024-08-30 16:02
Pay \ Element \ Allowance | The Pensionable Element "Add Prog Activity Long PAY NHS ARS" incorrectly contains 'NP' in the Reporting Name. |  | PRB2002816 | 2024-08-02 10:09
Pay \ Increments | Where a Bank assignment is included in the Bank Increment Process, but has not been granted an increment, the Bank Proposed Increment Date is incorrectly removed. |  | PRB2002729 | 2024-04-03 14:02 | 62.2.0.0
Pay \ P45 | When a User has been issued more than one P45, the 'View P45' Form is not displaying the P45 Issue/Issued Date. |  | PRB2002810 | 2024-07-29 10:26
Pay \ Pension \ Auto Enrolment | Pension Add Years deductions are being overstated in the period where absence is paid for Medical & Dental Staff. |  | PRB2002750 | 2024-05-17 10:03 | 63.0.0.0
Pay \ RTI \ EPS | An attempted submission of a historical EPS will result in the following error: "ava.sql.SQLException: ORA-20001: ORA-01858: a non-numeric character was found where a numeric was expected ORA-06512: at "APPS.PAY_GB_EPS_23", line 508 ORA-06512: at line 1". |  | PRB2002755 | 2024-05-23 14:26 | 63.0.0.0
Pay \ RTI \ FPS | HMRC are rejecting FPS XML submissions which contains an assignment that has been rehired prior to the Final Process Date of the original employment, with no gap in service and where full PAYE Aggregation is applied. | Y | PRB2002739 | 2024-04-29 16:31
Performance \ Data Warehouse | After a successful password reset, Users incorrectly receive the folllowing message. 'Login Failed PWD_RESET_OK' |  | PRB2002848 | 2024-09-20 10:56 |  | Y
Portal \ Configuration | Duplicate emails are being received for Liferay subscriptions which intermittently contain unwanted code "<esr_custom>" within the mail body. |  | PRB2002732 | 2024-04-11 09:53
Portal \ Dashboard | The BI Portlets on the Manager Dashboard intermittently do not render. |  | PRB2001458 | 2020-02-24 13:54
Portal \ Dashboard | Portal dashboard tabs are not aligned correctly when the Manage Internet Access button has been closed. |  | PRB2002707 | 2024-01-30 12:00
Portal \ Dashboard | Within the My Compliance portlet, the 'Play' button is incorrectly enabled for expired non-renewable Learning certifications. |  | PRB2002787 | 2024-06-26 10:12
Portal \ Dashboard | Within the My Compliance portlet, a duplicate competency is being displayed when a user is subscribed to multiple certifications which award the same competency. |  | PRB2002808 | 2024-07-25 12:06 | 62.3.0.0
Portal \ Dashboard | The Announcement banner within ESR is sized smaller than expected and consequently has a scroll bar on the right side of the banner. |  | PRB2002817 | 2024-08-05 13:38 | 62.2.0.0
Portal \ Dashboard | When accessing from My ESR Dashboard (where user has other URP as well as Employee Self Service), clicking the Back button re-directs user to the ESR Navigator page. |  | PRB2002834 | 2024-08-29 11:55 | 64.0.0.0
Reporting \ BI | Within the NHS Pensions Dashboard, the Pension Banding, Pension Banding Part Time & Pension Banding Unsocial Hours Analyses do not complete for large organisations. |  | PRB2002747 | 2024-05-09 15:46 | 62.3.0.0
Reporting \ BI | When a Vehicle Allocation record is retrospectively end dated, the records continue to be reported in BI. |  | PRB2002811 | 2024-07-29 12:21 | 62.3.0.0
Reporting \ BI | The Real Time Staff List (NHS Staff in Post Dashboard) is omitting assignments which have a previously end dated Budget Value Record. |  | PRB2002813 | 2024-07-31 08:30 | 62.2.0.0
Reporting \ BI | When a new permission is created for a BI Catalog Object, the User is presented with the facility to Apply Traverse Permission to parent folders even if the same account already has this permission through a different inherited privilege. |  | PRB2002820 | 2024-08-08 09:08 | 62.3.0.0
Reporting \ BI | When attempting to edit any variant of the following analyses, the user will receive an error message 'You do not have access privilege for this subject area': NHS Employment Checklist Dashboard - NHS Employment Checklist Detail, NHS Staff Requirements Dashboard - NHS Right to Work Detail. |  | PRB2002823 | 2024-08-12 09:33
Reporting \ BI | Within the NHS Workforce Profile Dashboard, the Online ESR Access summary analysis does not always complete for some larger organisations. |  | PRB2002825 | 2024-08-13 13:43 | 63.0.0.0
Reporting \ BI | Assignment FTE information that has been deleted in ESR is still available for reporting. |  | PRB2002829 | 2024-08-23 13:06 | 63.0.0.0
Reporting \ BI | Analyses based on the Workforce Profile Subject Area are not displaying the updated supervisor information when a supervisor is updated or removed from a non-primary terminated or terminated process assignment. |  | PRB2002832 | 2024-08-27 14:32 | 63.0.0.0
Reporting \ BI | The New Hire Form on the NHS HR Forms Dashboard does not return any data when selected. |  | PRB2002837 | 2024-08-30 16:07 | 62.3.0.0
Reporting \ BI | Where fields from the BABCP or BPS registration body folders within the 'Human Resources Person EIT Details' or Human Resources Applicant EIT Detail Subject Areas are included within an analysis, only employees/applicants with entries for those professional registration bodies are returned. |  | PRB2002839 | 2024-09-04 09:53 | 62.2.0.0
Reporting \ BI | Within the NHS Absence Dashboard, the Employee Absence report is returning an error message for large organisations. |  | PRB2002850 | 2024-09-20 15:51 |  | Y
Reporting \ BI | The 'Match Case' search option is incorrectly enabled by default for users resulting in case sensitive search results. |  | PRB2002851 | 2024-09-24 15:05 |  | Y
Self Service \ Employee | When requesting flexible working via Employee Self Service on a mobile device, users are unable to select a requested commencement date from the date picker’. |  | PRB2002748 | 2024-05-15 10:32
Self Service \ Employee | In the My Equality and Diversity portlet, the Country of Origin, Religious Belief and Sexual Orientation are not sorted in alphabetical order. |  | PRB2002819 | 2024-08-07 12:01 | 63.0.0.0
Self Service \ Employee | The Search button in the My Compliance portlet is incorrectly disabled when a learner has an enrolment status other than Confirmed against a class. |  | PRB2002826 | 2024-08-13 13:49 | 62.3.0.0
Self Service \ Employee | Leavers Dashboard access is incorrectly being assigned to new applicants where a historic termination exists against their person record. |  | PRB2002841 | 2024-09-05 10:40 | 62.3.0.0
Self Service \ Manager | When a manager hires an internal applicant using the replace primary assignment option and, the current primary assignment has a suffix e.g. -2, , then the primary assignment is set to the next available suffix. This occurs when there is an existing assignment with a higher suffix number than the Primary. |  | PRB2002506 | 2023-03-06 12:00
Self Service \ Manager | When replacing an active primary assignment with a Internal Secondment assignment the status is not updated to reflect the change. |  | PRB2002623 | 2023-08-31 12:34
Self Service \ Manager | When a Manager hires an Applicant and changes are made to the assignment, the current data is not displayed. Only the proposed changes are visible to review. |  | PRB2002754 | 2024-05-22 13:46

## Known Errors (with Workarounds)
Classification Description | Issue Description | Workaround | Problem Number | Date Identified | Proposed Release | New Addition
Absence \ Shared Parental Leave | When an employee is in receipt of both OSHP and SSHP and the combined amount exceeds their Normal Full pay amount, the payment of OSHP is not being reduced accordingly. | We advise the User to make an adjustment entry of overpayments using the 'Absence Manual Payment NPER NHS' element. | PRB2002824 | 2024-08-01 | 63.0.0.0
Learning Management \ Competencies | When a competence is added with dates that overlap an existing competency record within the competence profile, then a blank error message is displayed. This does not include narrative advising Users that the reason the record cannot be saved is due to the date overlap. | We advise Users to re-enter avoiding dates which overlap. | PRB2002219 | 2022-01-21 10:33
Pay \ RTI \ FPS | HMRC are rejecting FPS XML submissions which contains an assignment that has been rehired prior to the Final Process Date of the original employment, with no gap in service and where full PAYE Aggregation is applied. | Remove ALL assignment(s) in the FPS for the Employee record(s) causing the issue and retry the FPS to provide a new file that can then be submitted successfully. If not already done so, please raise an SR quoting PRB2002739 for assistance in identifying the termination causing the issue and advice on it's correction if required. | PRB2002739 | 2024-08-01

## Known Errors Data Warehouse
Classification Description | Issue Description | Workaround | Problem SR | Date Identified | Proposed Release | New Addition
Performance \ Data Warehouse | After a successful password reset, Users incorrectly receive the folllowing message. 'Login Failed PWD_RESET_OK' |  | PRB2002848 | 2024-09-20 10:56 |  | Y

## Closed Since Last Issue
Classification Description | Issue Description | Problem SR
Absence \ Annual Leave | The payroll run will return the following error when there are no payroll actions in the averaging period for AfC Average Pay: "Error was encountered when processing Element Type AfC Absence NHS Error was encountered when processing formula NHS_CALC_AFC_ASENCE The value returned from formula NHS_CALC_AFC_ABSENCE for AV | PRB2002705
Absence \ Annual Leave | When the Annual Leave Hours Accrual Plans is viewed on 31-Mar, and the length of service boundary affecting which rate to use also falls on this date, the entitlement is being overstated. | PRB2002781
Absence \ Unpaid Leave | When an Employee has an Absence the Pension Disallowed Days Balance is incorrectly using only the remaining days for the month of the initial submission date. | PRB2002757
HR \ IAT | The IAT Portable Data Set Copy is not completing for Delegate Bookings Details when the Delegate Contact Phone is more than 30 Characters. | PRB2002784
HR \ Person Record | The Professional Bodies Inbound Interface does not match records of person type 'EX_EMP_APL' when an application with a status of ("Preferred Applicant',' Offered Post Conditional', 'Offered Post Unconditional', 'Offer Accepted') is included in the file. | PRB2002741
Learning Management \ Catalogue \ Learning Certifications | Where several mandatory or optional classes have been added to a certification with varying dates and delivery methods there is no sort order applied. | PRB2001485
Learning Management \ Enrolment | Class enrolment notifications are not being sent to the learner, when the enrolment is made by a manager, supervisor or administrator onto an offering of type, “Online e-Learning” that requires approval. | PRB2002765
Learning Management \ Enrolment | When a learner views Classes attached to a Course, classes are not sorted on start date. | PRB2002783
Notifications \ Self-Service | Employees in Job Roles that have been renamed as part of National Workforce Data Set uplifts are not receiving 'Conflict of Interest Declaration' notifications. | PRB2002788
Pay \ Element \ Deduction | When an Annual Leave record with a reason of Bank Holiday is deleted, the AfC Average Pay makes an incorrect correction payment for the absence. | PRB2002708
Pay \ P45 | Where fully aggregated assignments are all terminated, then rehired fully aggregated, a P45 is not being issued for the terminated assignments. | PRB2002709
Portal \ Dashboard | Within the My e-Learning portlet, the 'Play' button is incorrectly enabled for expired Learning certifications. | PRB2002772
Reporting \ BI | The 'Employee Citizenship and Visa Permit' folder is incorrectly displayed to Users. | PRB2002782
Reporting \ BI | When a User creates a report based on the Human Resources - Archives Subject Area, a 'View Display' error is displayed. | PRB2002798
Reporting \ BI | Within the NHS Absence Dashboard, the Employee Absence report is returning an error message for large organisations. | PRB2002803
Reporting \ BI | The ‘Payroll Approval Role’ column, within the Organisation folder, does not return the correct data for some organisations when the Role Name has been updated/renamed. | PRB2002814
Self Service \ Employee | When an employee is terminated and then re-hired in a subsequent tax year, they cannot view their P60 for the year that the original termination date falls in. The following error is displayed, "Error: Temporary error connecting to backend system". | PRB2002809

## Closed Consolidated
Classification Description | Issue Description | Problem SR | Closed Month
Absence \ Annual Leave | When a User creates an Absence in Manage Self Service, the 'Submit' button needs to be pressed twice. | PRB2002393 | 2023-05-01
Absence \ Annual Leave | Users are not able to delete pending annual leave requests. | PRB2002616 | 2023-10-01
Absence \ Annual Leave | Bank Annual Leave Hours X NHS Carried Over elements are not available. | PRB2002659 | 2023-11-01
Absence \ Annual Leave | AfC Average payments are inaccurate when employees have been processed in a supplementary run, as only the supplementary run is taken into account, excluding the main run for the same period. | PRB2002717 | 2024-04-01
Absence \ Annual Leave | The date search facility on the Absence Summary Self Service screen does not return any results when searching for absences using a date range. | PRB2002670 | 2024-07-01
Absence \ Annual Leave | The payroll run will return the following error when there are no payroll actions in the averaging period for AfC Average Pay: "Error was encountered when processing Element Type AfC Absence NHS Error was encountered when processing formula NHS_CALC_AFC_ASENCE The value returned from formula NHS_CALC_AFC_ABSENCE for AV | PRB2002705 | 2024-09-18
Absence \ Annual Leave | When the Annual Leave Hours Accrual Plans is viewed on 31-Mar, and the length of service boundary affecting which rate to use also falls on this date, the entitlement is being overstated. | PRB2002781 | 2024-09-18
Absence \ Maternity | Statutory Maternity Pay entries are not always generated when an employee has adequate length of service and sufficient earnings in the Relevant Period to qualify for SMP Pay | PRB2001598 | 2022-01-01
Absence \ Maternity | The NHS Maternity Entitlement Letter does not include the value of OMP Corrections in OMP Full amount. | PRB2002581 | 2023-09-01
Absence \ Maternity | When an employee has periods of long term absence such as maternity, adoption, long term sickness, these are not being excluded from the AfC Average Reference period, | PRB2002481 | 2024-01-01
Absence \ Paternity | The ‘SPP Absence NHS’ element is being incorrectly processed in some scenarios where ‘Date To’ value is prior to the start date of the pay period and the element has not been end dated by the user beyond the ‘Date To’ value. | PRB2001820 | 2022-01-01
Absence \ Paternity | When entering a Paternity Birth record with a PPP Start Date more than 49 days after the Expected Week of Childbirth, the following error occurs: "APP-SSP-36097: The Start Date of the Paternity Pay Period must not be later than 49 days after the birth date, for normal births. For babies born before Expected Week of Childbirth, the start date must not be later than 49 days after the Expected Week of Childbirth." | PRB2002725 | 2024-04-01
Absence \ Shared Parental Leave | When creating evidence in Shared Parental Leave if the Request Date is later than the Received Date then the following error occurs 'SSP_36870_INV_EVD_RQST_DATE.' | PRB2001982 | 2023-03-01
Absence \ Shared Parental Leave | Users are unable to create a Shared Parental Absence record with the same Due Date as that of the Maternity record. | PRB2002006 | 2023-07-01
Absence \ Shared Parental Leave | Users will receive the error: "Absence ID not found on Attribute 19" when absences related to SHPL have been deleted and then recreated. | PRB2002536 | 2024-01-01
Absence \ Shared Parental Leave | The Occupational Shared Parental Pay does not reflect the mid-absence average earnings update. | PRB2002548 | 2024-01-01
Absence \ Sickness | When a Sickness Absence is amended for terminated assignments which results in OSP Half Pay entries, then an incorrect payment can be made (when Retropay is run). | PRB2002212 | 2022-10-01
Absence \ Sickness | Absence is present in the Employees Absence Calendar can be missing from the Absence Summary screen. | PRB2002244 | 2022-10-01
Absence \ Sickness | When a Sickness Absence Start Date falls on the same date as a pay date, the earnings for that pay date are incorrectly included in the Average Weekly Earnings calculations. | PRB2001817 | 2023-03-01
Absence \ Sickness | When updating an earlier sickness absence, an Oracle exception message will be displayed and the absence will be given a status of Work In Progress. | PRB2001951 | 2023-03-01
Absence \ Sickness | The SSP payment may be incorrect when a retrospective change is made to the end date of the sickness record leading to multiple statutory sick pay elements with the same start date. | PRB2002198 | 2023-08-01
Absence \ Sickness | In certain scenarios employees who have an open ended AfC Absence can be incorrectly subject to correction in a subsequent pay period. | PRB2002638 | 2023-11-01
Absence \ Sickness | Employers Pensionable Pay not calculating correctly when employee is in receipt of Statutory Sick Pay only. | PRB2002538 | 2024-01-01
Absence \ Sickness | The NHS OSP Batch Process is not taking into account the days that are already paid for the current work related Sickness resulting in the incorrect OSP entry calculation. | PRB2002714 | 2024-04-01
Absence \ Special | An erroneous payment may arise for Shared Parental Leave made beyond the 39 week qualifying period. | SR1697369 | 2022-12-01
Absence \ Unpaid Leave | When multiple changes are made to an Unpaid Absence in the same payroll period prior to processing, the most recent update removes the previously entered corrections waiting to be processed. | PRB2002596 | 2024-01-01
Absence \ Unpaid Leave | When an Employee has an Absence the Pension Disallowed Days Balance is incorrectly using only the remaining days for the month of the initial submission date. | PRB2002757 | 2024-09-18
Access Security \ ESR Via a PC/Laptop | When a user session times out and they attempt to resume, 2 login screens are displayed one on top of the other. | PRB2002432 | 2023-02-01
Application \ Access | Smartcard users are unable to resume their session on the last accessed page after a session timeout occurred. | PRB2001917 | 2022-01-01
Application \ Access | The NHS Pensionable Pay Report OSP Nil data is misaligned and displays in the OMP field. | PRB2002017 | 2022-01-01
Application \ Access | User not able to update contact details via My Personal Information Portlet where the Primary Address does not match their Home Address. | PRB2002069 | 2022-12-01
Application \ Access | When a user launches BI through Oracle forms, an additional window appears. This has been detected in the Microsoft Edge and Google Chrome browsers. | PRB2002288 | 2022-05-01
Application \ Access | When a Smartcard User resumes their session having been in the Org Chart screen, an additional embedded window is displayed. | PRB2002438 | 2023-12-01
Application \ Configuration | In the My Appraisal and Review portlet, the value 'None Recorded' is not aligned correctly when viewed on a mobile device. | PRB2002218 | 2022-05-01
Application \ Configuration | Welsh Organisations are unable to navigate to the Professional Dashboard via the Portal Site Administration URP. | PRB2002594 | 2023-09-01
ESR | When submitting a Copy Single Request, the Find function returns an error. | PRB2001043 | 2022-12-01
ESR | Where Users have multiple Bank Payments set up in the Manage Payroll Payments: Define Payment page an error is displayed when updating the 2nd Bank Payment 'An error occurred: please verify your login information or contact your ESR Administrator' | PRB2001838 | 2023-02-01
HR | When exporting data from the Enter HR Personal Information form, the Web ADI Integrator screen will display a session date which defaults to a day behind the current date, although the exported session date will be correct. | PRB2000491 | 2023-01-01
HR \ Assignments | When accessing Apprenticeship Details Extra Information in Assignment Extra Information Form the following message is displayed: 'Oracle - ORA-01840 Input Value not Long Enough for Date Format) However Users can click OK and continue. | PRB2002278 | 2022-05-01
HR \ Assignments | When accessing the 'Apprenticeship Details' EIT the following error message can be displayed: 'Oracle - ORA-01840 Input Value not Long Enough for Date Format)'. However Users can click OK and continue. | PRB2002294 | 2022-07-01
HR \ Assignments | When accessing the 'Apprenticeship Details' EIT the following error message is displayed. ''ORA-01840 Input Value not Long Enough for Date Format)'. Where data exists within the EIT it will not be visible to users. When accessing the ‘RTI Information’ and ‘RTI Migration Information’ a different error message is display | PRB2002337 | 2022-10-01
HR \ Assignments | When uploading a picture file which contains a virus the following error is produced: 'Message not found. Application: XXH, Message Name: XX_HR_EMPDIR_IMAGE_TYPES.' This occurs using the following path: XXX HR Administration > Others > Picture. A more pertinent message should be displayed.' | PRB2000178 | 2023-02-01
HR \ Assignments | Date tracked changes to a Position Title are not always correctly reflected in Manager Self Service. | PRB2002025 | 2023-03-01
HR \ Assignments | When terminating applicants with a person type of Employee.Applicant this incorrectly end dates the Budget Values for the assignment. | PRB2002352 | 2023-05-01
HR \ Assignments | The Position Name does not in all cases conclude with a trailing '¦' (Pipe Character) | PRB2001507 | 2023-07-01
HR \ Assignments | Information messages are not being displayed correctly on the Search ESR page | PRB2002542 | 2024-01-01
HR \ Competencies | If a Competence Requirement is set at Business Group level and removed at Position Level it removes the Competence Requirement from the Business Group level. | SR1057935 | 2023-01-01
HR \ Hires/Rehires | Users are unable to hire internal applicants with a recent termination date, where the final process date for the previous employment has not been set. | PRB2002102 | 2023-01-01
HR \ IAT | The Type field for External Learning is not included in the PDS copy | PRB2001824 | 2023-01-01
HR \ IAT | User can receive a notification advising Competence Updates have failed during an IAT where the parent IAT has been cancelled or completed error. | PRB2001932 | 2022-01-01
HR \ IAT | IAT process fails with a User Defined Exception with Competences that have been incorrectly created by the pre-IAT process | PRB2002287 | 2022-10-01
HR \ IAT | When hiring applicants concurrently, the prompt to complete the IAT Portable Data Set Copy is incorrectly displayed for the second and subsequent applicants. | PRB2002387 | 2023-01-01
HR \ IAT | The IAT PDS Copy Fails when there is an open-ended Competency in the Source Employees' Competency Profile as the Competency itself is End Dated. | PRB2002450 | 2023-03-01
HR \ IAT | The Leaving Reason is omitted from the IAT Service History Notification when an employee is rehired, and subsequently terminated. | PRB2001333 | 2023-08-01
HR \ IAT | The IAT initiation process will fail where a person's 'First Name', 'Last Name' or 'Known As' are greater than 30 characters. | PRB2002551 | 2023-09-01
HR \ IAT | The IAT process will fail if the person in the source organisation has no email address entered. | PRB2002774 | 2024-07-01
HR \ IAT | The IAT Portable Data Set Copy is not completing for Delegate Bookings Details when the Delegate Contact Phone is more than 30 Characters. | PRB2002784 | 2024-09-18
HR \ Letters | Position Iinformation.is currently missing from the Welsh Reference letter. | PRB2001678 | 2023-02-01
HR \ Letters | During the Web ADI Export, the Session Date within the Select Content Parameters screen is set to the form's Session Date minus 1 day. | PRB2002779 | 2024-07-01
HR \ Person Record | The validation error message for the Registration Number for the General Dental Council Prof Reg Body is showing the value code rather than the value meaning. | PRB2002310 | 2022-11-01
HR \ Person Record | When attempting to Rehire a Person that has a future dated person type change, the following error will be produced. 'APP-PAY-07193: You cannot continue with this change future person types exist' | PRB2001294 | 2024-01-01
HR \ Person Record | The Professional Bodies Inbound Interface does not match records of person type 'EX_EMP_APL' when an application with a status of ("Preferred Applicant',' Offered Post Conditional', 'Offered Post Unconditional', 'Offer Accepted') is included in the file. | PRB2002741 | 2024-09-18
HR \ Recruitment \ Applicants | The Applicant Purge process is not purging applicants where the last_updated_by or created by is not populated. | PRB2002322 | 2022-10-01
HR \ Recruitment \ Applicants | The Auto IAT Process can result in an invalid e-mail address being transferred, which are those that do not end with '.nhs.net' at the pre-hire stage. | PRB2002706 | 2024-05-01
HR \ Terminations \ Employee | Within Self Service, when an employee is terminated with a future date, the email address is incorrectly removed at the point that the termination record is Saved. | PRB2001407 | 2022-01-01
HR \ Terminations \ Employee | The exit questionnaire notification isn’t being generated for assignments with an assignment status of ‘Suspend No Pay’ or ‘Suspend with Pay’. | PRB2002681 | 2024-08-01
HR \ Work Structures \ Hierarchy | Proxy Users are not able to view subordinates in the Absence Calendar hierarchy. | PRB2000807 | 2022-12-01
HR \ Work Structures \ Positions | On a Position, the 'Shared' type allows the addition of people above the value defined in the FTE field. | PRB2002266 | 2023-01-01
Interfaces \ e-Recruitment | The Bi-Directional e-Rec Outbound Interface is incorrectly including application records which are no longer active. | PRB2002035 | 2022-01-01
Interfaces \ e-Recruitment | Where multiple rows exist in the 'Employment Checklist Details’ EIT then the Employment Checks Interface is rejecting the record. | PRB2002036 | 2022-01-01
Interfaces \ e-Recruitment | Applicant records are incorrectly being matched to External Learner records by the e-recruitment inbound interface, meaning they can't be hired as an employee. | PRB2002237 | 2022-09-01
Interfaces \ e-Recruitment | Terminated External Learner records are incorrectly being included in the e-recruitment inbound interface | PRB2002569 | 2023-10-01
Interfaces \ e-Recruitment | The NHS e-recruitment Inbound Interface incorrectly creates a New Applicant Record instead of updating the existing Employee record when the NI Number is not given in the file. | PRB2002727 | 2024-06-01
Interfaces \ e-Recruitment | The Employment Checks Outbound Interface is incorrectly sending out data for employees who no longer have an active Applicant Assignment. | PRB2002775 | 2024-08-01
Interfaces \ General Ledger (GL) | Users are unable to enter Local GL Cost Mappings for the ''GLMAP Recovery Notional SHPP' Element'. | PRB2002649 | 2023-11-01
Interfaces \ Other | The Professional Registration and Full Registration Date fields do not contain the Time component loaded via the NHS Professional Body Interface. | PRB2001809 | 2024-04-01
Interfaces \ Professional Registration Bodies (NMC/GMC) | The Professional Bodies interface fails to update EIT records where the 'E-Rec Vacancy Ref' no longer exists in ESR. | PRB2002599 | 2023-11-01
Learning Management | In Employee Self Service when performing an Exact Phrase search in My Learning which contains the - (minus / hyphen) character an error page is displayed. | PRB2000963 | 2023-01-01
Learning Management \ Catalogue \ Learning Certifications | When an applicant completes a Learning Certification the competence is updated automatically without going for approval, when the Learning Certification Competence Update setting is 'Notification, Automatic Update after approval'. | PRB2001814 | 2023-02-01
Learning Management \ Catalogue \ Class | Duplicate enrolments can be created by the Learning Auto Enrolment and Subscription process where a competence requirement has been added with a future date and an employee has multiple assignments with the same requirement. | PRB2002279 | 2022-10-01
Learning Management \ Catalogue \ Class | Users can encounter the following error message when using Learning Administration / Manager Self Service: ’Error cannot display page’. If a User subsequently retries the action this will be successful. | PRB2002298 | 2022-10-01
Learning Management \ Catalogue \ Course | Pictures are not retained for more than 24 hours when they have been attached to Courses | PRB2001686 | 2022-10-01
Learning Management \ Catalogue \ Course | The NHS End Date/Close Course, Offering, Class process is not working | PRB2002521 | 2023-07-01
Learning Management \ Catalogue \ Learning Certifications | Users are only able to delete one subscription from the Learning Certification Subscriptions page, even when multiple subscriptions are selected. | PRB2001812 | 2022-01-01
Learning Management \ Catalogue \ Learning Certifications | Within the Learning Certification Options Available page, the Play button is incorrectly available for Content that has reached the maximum number of plays without renewals. Clicking this play button will result in a Java error being displayed. | PRB2002746 | 2024-08-01
Learning Management \ Catalogue \ Learning Certifications | Where several mandatory or optional classes have been added to a certification with varying dates and delivery methods there is no sort order applied. | PRB2001485 | 2024-09-18
Learning Management \ Catalogue \ Offering | OLM emails are sent with incorrect formatting and HTML characters when sent as plain text. | PRB2002457 | 2023-02-01
Learning Management \ Class Administration | When adding a class to ESR and specifying the start time, the time displayed in in the MyESR Calendar Portlet as + 1 hour. | PRB2002347 | 2022-11-01
Learning Management \ Class Administration | Users are unable to copy a class that has a venue attached. | PRB2002532 | 2023-10-01
Learning Management \ Competencies | The Existing Job Competency Requirement can be incorrectly duplicated to the corresponding Position. | PRB2001760 | 2022-02-01
Learning Management \ Competencies | When a Learning Certification is created with only Optional courses, i.e. no Mandatory courses, any competencies attached to the Learning Certification will not be awarded when the user updates their status to Certified. | PRB2002043 | 2022-07-01
Learning Management \ Competencies | The IAT process can fail to complete whilst copying competence data where an employee is hired back into the same Organisation after previously retiring. | PRB2002181 | 2023-01-01
Learning Management \ Competencies | The My Compliance Portlet incorrectly displays the same competency multiple times when the Learning Certification contains a classroom based course with multiple classes attached. | PRB2002461 | 2023-03-01
Learning Management \ Content \ Play | The Home button is not visible on the mobile devices when accessing e-learning courses and this prevents updates to tracking and progress are not visible on the mobile devices when accessing e-learning courses. | PRB2002245 | 2022-11-01
Learning Management \ Enrolment | Employee Self Service users are directed to the Offering page, even when only one of the offerings available has classes attached. | PRB2001453 | 2022-12-01
Learning Management \ Enrolment | The Search and Select windows in SSHR and OLM opens as a new window and not as 'pop-up' as expected. This has reverted to the pre 2021 display. | PRB2002005 | 2022-05-01
Learning Management \ Enrolment | Auto-enrolment does not work where an applicant record is created via the Applicant Quick Entry Form with an initial status of ‘Offer Accepted’. If an alternative value is selected and then subsequently changed to ‘Offer Accepted’ then the applicant will be included in auto-enrolment. | PRB2002243 | 2022-05-01
Learning Management \ Enrolment | The email notification 'Update of Training Information' is not produced when updates are made to a class date, time or venue details. | PRB2002293 | 2022-09-01
Learning Management \ Enrolment | The Person Type field in the Enrolments and Subscriptions search is displaying duplicate values | PRB2002570 | 2023-09-01
Learning Management \ Enrolment | When a Learning Administrator tries to bulk subscribe and enrol employees within a Learner Group onto a Learning Path and associated courses the process fails to complete, and employees are not enrolled.” | PRB2002524 | 2023-10-01
Learning Management \ Enrolment | In the Update Attendance Portlet, the warning message advising administrators to manage enrolments in EBS when the number of attendees is greater than 50 is not displayed. Administrators will still need to manage the enrolments in EBS where this is the case. | PRB2002641 | 2024-04-01
Learning Management \ Enrolment | When a learner is unsubscribed and then immediately subscribed to a Learning Certification via the Search and View Learner functionality, an Oracle message is returned containing the text 'stale data' | PRB2002520 | 2024-06-01
Learning Management \ Enrolment | When clicking on the 'Add to Outlook' button on the 'Enrolments' tab of the Learner Homepage, the following error is displayed 'The item you are trying to export has missing data such as no end-date and cannot be exported'. | PRB2002660 | 2024-07-01
Learning Management \ Enrolment | When enrolling onto a course from a Shared Training Provider that will change the Class Status to 'Full', the following error is displayed, 'You are not allowed to modify or delete this value as it does not belong to the Trust under which you are currently working.' | PRB2002745 | 2024-08-01
Learning Management \ Enrolment | External Learning Classes are incorrectly being sent for approval when actioned by a User with the Learning Administration URP through the 'Search and View Learner' page. | PRB2002789 | 2024-08-01
Learning Management \ Enrolment | When a User is enrolling onto a certification, courses that have an end-date in the past are incorrectly visible to enrol in. | PRB2002795 | 2024-08-01
Learning Management \ Enrolment | Class enrolment notifications are not being sent to the learner, when the enrolment is made by a manager, supervisor or administrator onto an offering of type, “Online e-Learning” that requires approval. | PRB2002765 | 2024-09-18
Learning Management \ Enrolment | When a learner views Classes attached to a Course, classes are not sorted on start date. | PRB2002783 | 2024-09-18
Learning Management \ Learning History | When successfully completing a course that is stored via Learning Certification, the learner's score is not populated on their Learner Homepage. | PRB2002048 | 2023-01-01
Learning Management \ Learning History | Learning Administrators are unable to update user competences using the Compliance and Competency form and an error is displayed which contains 'This transaction cannot be completed as there is no Supervisor/Manager linked to your ESR record…'. | PRB2002766 | 2024-07-01
Monitoring \ Process \ Failure | The NHS GO2 Interface can fail to produce expected file outputs in a timely manner resulting in delays in provision of updates to Users. | PRB2002312 | 2023-01-01
Monitoring \ Process \ Failure | The NHS Payslip availability notification emails sometimes are not being generated for some employees. | PRB2002316 | 2022-08-01
Monitoring \ Process \ Failure | The NHS Employment Checks People and User Refresh process does not in all cases complete. | PRB2001176 | 2023-02-01
Monitoring \ Process \ Failure | Due to invalid email address the Competence Expiry, Registration Expiry and Review Due Notifications fails to complete leading to additional duplicate notifications being generated for organisations or notifications being delayed. | PRB2002522 | 2023-06-01
Notifications | Workflow notification emails are not being distributed to ESR Users in a timely manner at the beginning of each month. When a notification is approved in ESR prior to the email being generated the email is not sent in all cases. | PRB2002014 | 2023-01-01
Notifications | The notifications for “Review your Equality and Diversity Information” and “Review your Personal Details” are not being sent via email. Additionally the organisation name within the notification’s text is returning the assignment level organisation rather than the Trust level organisation. [Now being tracked under PRB2002663] | PRB2002531 | 2023-10-01
Notifications | The notifications for “Review your Equality and Diversity Information” and “Review your Personal Details” are not being sent via email. | PRB2002663 | 2024-08-01
Notifications \ Absence | When an Absence Annual Leave is created by an employee, and a Manager / Administrator deletes the request, the employee received a rejection notification instead of a deletion notification. | PRB2001582 | 2023-06-01
Notifications \ Absence | Leave of Absence Self service failing after being returned for correction and a correction made | PRB2002575 | 2023-11-01
Notifications \ Absence | The Maternity Return Date Notification can incorrectly include records of previous periods of Maternity, which display with the previous period start date and the current period's end date. | PRB2002633 | 2023-11-01
Notifications \ Absence | The iCalendar attachment is not available on absence notifications when the Absence Reason is not populated. | PRB2002675 | 2024-03-01
Notifications \ Appraisals | Appraisal Comments entered in the 'Overall Objective Information' section are not being displayed. | PRB2000175 | 2022-02-01
Notifications \ Appraisals | When viewing a series of Completed Appraisals, each Appraisal will show the Employee Details (e.g. Name, Number) of the first selected, though the Appraisal Details will relate to the selected Employee. | PRB2000299 | 2022-12-01
Notifications \ Appraisals | When using the Upload to Journal functionality via the Appraisals pages, the following error message is displayed: 'The antivirus software could not be run on the attachment XXXXXX. Please disable virus scanning or contact your system administrator for further assistance'. | PRB2002117 | 2023-01-01
Notifications \ Competencies | Expiry Notifications are not being generated for employees where their assignment status is anything other than 'Active Assignment' or 'Suspend No Pay'. | PRB2002700 | 2024-07-01
Notifications \ HR | Projected New Starter Notification can contain duplicate rows for assignments. | PRB2002059 | 2022-03-01
Notifications \ HR | Payroll approval notifications can be incorrectly cancelled by 'Anonymous' or 'National Request' Users. | PRB2002106 | 2022-05-01
Notifications \ HR | The "Registration Expiry Notification Workflow" does not generate Short Notice notifications for employees with multiple professional body records, whose expiry date may have been updated to within the short notice period, for multiple records on the same day. | PRB2002135 | 2022-05-01
Notifications \ HR | User are incorrectly being returned to the worklist when ticking the 'Display Next' checkbox within Workflow Worklist instead of displaying next notification. | PRB2002204 | 2022-10-01
Notifications \ HR | The presence of multiple '&' characters in the position title causes an error in the pay progression notification. | PRB2002236 | 2023-01-01
Notifications \ HR | An additional exit questionnaire can be sent when a terminated assignment has a subsequent status change from Process Terminate Assignment to Terminate assignment. | PRB2002300 | 2022-10-01
Notifications \ HR | The 'Right to Work Document Expiry' notifications will produce a notification with headings only and no details, when the field 'Source Document Checked' has not been populated in the 'Illegal Working Checklist' EIT. | PRB2002508 | 2023-06-01
Notifications \ HR | Managers and Role Holders incorrectly receive Flexible Working notifications and e-mails for ex-employees. | PRB2002763 | 2024-08-01
Notifications \ Payroll \ HMRC Generated | When loading a PGL2 XML file, the file is remaining at status of 'Loaded in Interface Table' and not applying a stop date to the affected Assignments for the Postgraduate Loan element. | PRB2002676 | 2024-04-01
Notifications \ Self-Service | Payroll approval role holders are receiving duplicate emails when only one actionable worklist notification has been sent. | PRB2002124 | 2022-03-01
Notifications \ Self-Service | Searching by Start Date or End Date on the Learner Groups table will not return any results, instead the message ‘No Results Found’ will be displayed in the results table. Using the Query by Example functionality on the Search ESR table will not return any results, instead the message ‘No Results Found’ will be displa | PRB2002160 | 2023-01-01
Notifications \ Self-Service | The Request to Update Personal Information notification sent to the Applicant Details role holder is displaying N/A in place of Applicant Name (Applicant Number) value. In addition, the Applicant Name is not displayed in the body of the notification. | PRB2002486 | 2023-05-01
Notifications \ Self-Service | An additional exit questionnaire can be sent when a terminated assignment has a retrospective change. | PRB2002513 | 2023-09-01
Notifications \ Self-Service | When attempting to open a FYI Termination notification generated for an employee termination request created in Manager Self-Services the following error is produced: 'You have encountered an unexpected error. Please contact your System Administrator for assistance.’ | PRB2002504 | 2024-05-01
Notifications \ Self-Service | The URL in the "Review Your Equality and Diversity Information" notification incorrectly sends the user to the My Personal Information portlet instead of the My Equality and Diversity portlet. | PRB2002712 | 2024-05-01
Notifications \ Self-Service | Employees in Job Roles that have been renamed as part of National Workforce Data Set uplifts are not receiving 'Conflict of Interest Declaration' notifications. | PRB2002788 | 2024-09-18
Pay \ Bank Details \ Sortcode | The IAT process does not always transfer the latest bank account details from the source record. | PRB2002131 | 2022-01-01
Pay \ Batches \ Batch Summary | When exporting the Batch Element Summary will fail when the data contains Annual Leave Carry Over elements. | PRB2002550 | 2023-07-01
Pay \ Batches \ Web ADI | The Web ADI Pay Method Upload facility returns an error for assignments that are attached to a Payroll which has a Name exceeding 30 characters in length. | PRB2002430 | 2023-03-01
Pay \ Costing | Users are currently unable to separately cost the Balance Sheet value of the 'ShPP Rebate' element. | PRB2002033 | 2023-08-01
Pay \ Costing | The Postgraduate Loan Arrears Element is currently not enabled for Costing in ESR thereby impacting the GL Interface. | PRB2002651 | 2023-11-01
Pay \ Element \ Allowance | An incorrect value for Short Term Enh Protection can arise in a pay period where there is a mix of OSP Full, Half or Nil elements present, and the enhancements paid in that period exceed the prorated protected amount. | PRB2001470 | 2022-12-01
Pay \ Element \ Allowance | The new Salary Sacrifice Grp 0RBAL NHS elements are taking deductions from Gross Pay when the assignment status is Maternity and Adoption. | PRB2002122 | 2022-01-01
Pay \ Element \ Allowance | The NHS Pensions Agency Bank Leaver Interface - Update Element Entries and Assignments process can incorrectly update the assignment status for assignments which have been processed by the NHS Pension Agency Bank Leaver Interface in a prior year when the Assignment was set to an 'Inactive'. | PRB2002311 | 2023-01-01
Pay \ Element \ Allowance | The Non Consol Payment NR NP NHS element arising from the Pay Award can produce an incorrect Pay Value in certain scenarios when an assignment has had a change in Standard Working Hours on 31-MAR-2023. | PRB2002574 | 2023-09-01
Pay \ Element \ Allowance | When a date track update is made to the AfC Average Pay NHS element, that date is incorrectly used as the start date for the assignment's eligibility for AfC Average Pay rather that the true start date of the element. | PRB2002530 | 2024-01-01
Pay \ Element \ Allowance | Where the Sickness Stop NHS element is attached to an assignment, this will prevent AfC Average payments from being generated for both sickness and annual leave. | PRB2002661 | 2024-04-01
Pay \ Element \ Deduction | The Direct Earnings Attachment NTPP element is deducting an incorrect amount, where the entry values have been changed to include a Fixed Deduction and the assignment also has a Court Order attached. | PRB2002034 | 2022-05-01
Pay \ Element \ Deduction | When a fully aggregated employee with a Direct Earnings Attachment Order against multiple assignments is paid on the supplementary run, the deductions taken are incorrectly refunded. | PRB2002156 | 2023-01-01
Pay \ Element \ Deduction | 'Unpaid Hours Absence' type does not allow more than one type to be entered with the same absence date. | PRB2002514 | 2023-06-01
Pay \ Element \ Deduction | When an employee has multiple assignments, then the calculation for Court Order Deductions can be incorrect for Child Maintenance Deductions. | PRB2002480 | 2023-12-01
Pay \ Element \ Deduction | When an assignment has both a pro ration event on basic pay and a salary sacrifice deduction in the same period, a payslip message regarding a breach of the National Minimum/ Living Wage is incorrectly displayed. | PRB2002738 | 2024-08-01
Pay \ Element \ Deduction | When an Annual Leave record with a reason of Bank Holiday is deleted, the AfC Average Pay makes an incorrect correction payment for the absence. | PRB2002708 | 2024-09-18
Pay \ Element \ NI | The NHS Update NI Category Process is not updating the NI category from 'A' to 'C' for some employees when they reach state pension age. | PRB2002290 | 2022-10-01
Pay \ Element \ NI | The RTI GB Update NI Category completes with a status of 'Warning' when trying to update the NI Category for an aggregated employee in a designated Freeport Area. | PRB2002263 | 2023-07-01
Pay \ Elements Pension | 'The 'Locally Agreed Notional NT NNI NHS’ element is not feeding the LGPS Pensionable Pay balances. | PRB2000133 | 2023-10-01
Pay \ Increments | The Bank Increment Process is using an incorrect value for Bank Hours Worked where assignments have been transferred between payrolls and the payroll start date is after the increment date | PRB2000711 | 2022-12-01
Pay \ P11D | The P11D Report (pdf) and the NHS P11D List Report can overstate the Total Cash Equivalent for Cars for a proportion of assignments. | PRB2001177 | 2022-12-01
Pay \ P11D | A P11D will not be generated for an Employee with P11D entries against 2 assignments and and the benefit value of 2nd assignments is '0'. The P11D can be generated using an assignment set as proposed workaround. | PRB2001963 | 2022-05-01
Pay \ P11D | The 'NHS Payrolling of Benefits in Kind NIC Report' excludes Mid-Year Leavers. | PRB2001967 | 2022-12-01
Pay \ P11D | The Employee Number is missing from the P11D Archive for ex-employees whose final process date is before the benefit year end date. | PRB2002016 | 2022-05-01
Pay \ P11D | When a P11D is requested, and the double sided print option is selected with the worksheet printing parameter set to 'None', in some cases additional blank pages are being generated which moves the address details incorrectly onto another sheet. | PRB2002338 | 2023-05-01
Pay \ P11D | When correcting a form P11d for a previous year related to an employee's car record, the P11d Report is completing in Error . | PRB2002354 | 2023-05-01
Pay \ P11D | The P11d Reports process may produce the P11d in three pages, instead of two, if a single word entered within the 'Make and model' field exceeds 21 characters. | PRB2002540 | 2024-02-01
Pay \ P11D | The P11D PDF output is not being generated for terminated employees who left in the 2023/24 tax year and are due a P11D. | PRB2002769 | 2024-06-01
Pay \ P45 | Where fully aggregated assignments are all terminated, then rehired fully aggregated, a P45 is not being issued for the terminated assignments. | PRB2002709 | 2024-09-18
Pay \ P60 \ On Line | When the NHS RTI NI Reporting assignment has been terminated but has not been ended within the same tax year then the Assignment NI details are not reported on the P60. | PRB2002141 | 2022-05-01
Pay \ P60 \ On Line | When an employee tries to download their P60, having already visited the link, they are unable to do so. Additionally when downloading more than one P60, the year of the first document selected will be used as the name for all. However, the information in each P60 is correct. | PRB2002485 | 2023-05-01
Pay \ P60 \ Process | The RetroPay By Element Output Log is not returning all of the expected data. | PRB2001505 | 2022-02-01
Pay \ P60 \ Process | When an employee's NI Aggregation status is changed on a date other than the 6th April can cause errors is NHS RTI FPS / EYU processes and may also impact Forms P60. | SR1689640 | 2022-05-01
Pay \ Payroll Cycle | Average Earnings for Statutory Maternity Pay purposes will not be calculated where an employee has multiple assignments, the latest of which has not been processed in the payroll period immediately prior to the relevant period for SMP. | PRB2002041 | 2022-01-01
Pay \ Payroll Cycle | The OSHP entries are incorrectly created against the non-primary assignment when the primary assignment is changed between MPP Start Date and SPL Start Date. | PRB2002077 | 2022-01-01
Pay \ Payroll Cycle | The Pension re-banding process is not applying the new band from the correct date in all scenarios where there are multiple assignment changes. | PRB2002121 | 2022-07-01
Pay \ Payroll Cycle | When the RTI GB Update NI Category process updates an assignment to be on NI category C, it is populating the Certificate field on the NI Details form with 'Age to be Verified', despite the employee having the date of birth verified date populated. | PRB2002207 | 2022-03-01
Pay \ Payroll Cycle | When an NI Aggregated employee with assignments on cross frequency payrolls has NI Category amended to 'C' from their State Pension Age date, the Retropay by Element and Payroll run on the monthly assignment can error with the following error message: 'NI_PERSON: This is not a valid combination of NI Categories for Agg | PRB2002151 | 2023-03-01
Pay \ Payroll Cycle | When submitting Payroll Run concurrent requests, the Payroll default does not always select the first Payroll Name in the list, which may lead to an inactive Payroll being presented | PRB2002426 | 2023-08-01
Pay \ Pension \ Auto Enrolment | Non-Recurring payments, which continue to be paid during periods of sickness, are not being considered during the Pension Added years calculation. | PRB2002187 | 2022-10-01
Pay \ Pension \ Auto Enrolment | The NHS Monthly Summary for Pension Schemes report is incorrectly excluding the ERRBO contributions for some terminated employees, from the YTD totals. | PRB2002274 | 2022-05-01
Pay \ Pension \ Auto Enrolment | The NHS Pensions Rebanding Assessment Process is outputting a misleading message of 'Skipped, no pay affecting changes' when an assignment is assessed but a banding change is not required. | PRB2002529 | 2024-01-01
Pay \ Pension \ Auto Enrolment | The Mid-Year pension reassessment process does not asses the contribution rate where an employee has multiple salary sacrifice entries in a single period. | PRB2002628 | 2024-04-01
Pay \ Retropay | Retropay can error where the Court Order element is processed for an employee who has had a second assignment added after the initial entry of element and the DEO Overriding Frequency value has not been entered. | PRB2002232 | 2022-07-01
Pay \ Retropay | Retropay is generating refunds where the processes calculating that there is insufficient net pay to make a deduction. | PRB2002253 | 2022-05-01
Pay \ Retropay | When an NI Aggregated employee with a monthly and weekly assignment has been amended to NI Category C from their State Pension Age date, the Retropay by Element process on the weekly assignment can error with the following error message: NI_PERSON: This is not a valid combination of NI Categories for Aggregation. | PRB2002560 | 2024-05-01
Pay \ RTI \ EYU | The NHS RTI EYU XML Process 2018/19 returns errors for terminated assignments with a Balance Adjustment dated 31st March 2019. | PRB2002271 | 2022-07-01
Pay \ RTI \ EYU | The NHS RTI FPS Amendments XML Process 2019/20 is being rejected by the HMRC with the following error message: Invalid content found at element 'SPBPYTD'. | PRB2002295 | 2022-07-01
Pay \ RTI \ FPS | The New Starter Declaration is incorrectly set to Null for some assignments which prevent the submission of the NHS RTI FPS for the employees affected. | PRB2001044 | 2022-01-01
Pay \ RTI \ FPS | The NHS RTI FPS excludes person level NI balances for an employee who has multiple assignments and is a late leaver. | PRB2001229 | 2022-12-01
Pay \ RTI \ FPS | The NHS RTI FPS process related to a Supplementary Payroll Run can incorrectly report Negative NI values to HMRC for some assignments. | PRB2001669 | 2022-01-01
Pay \ RTI \ FPS | When an employee has multiple assignments, and the employee is unaggregated as at 6th April, PAYE is calculated on individual assignments rather than collectively. The new starter declaration box is unticked on one assignment which causes the FPS to error. | PRB2001685 | 2022-12-01
Pay \ RTI \ FPS | The NHS RTI FPS Amendments XML Process 2019/20 will fail to complete when an employee has a new payroll ID and is subsequently switched back to the original payroll ID within the tax year. | PRB2001776 | 2022-02-01
Pay \ RTI \ FPS | Assignment Number, NI Number & Employee Name are omitted from the Error section of the NHS RTI Additional FPS XML Process (Terminate Aggregate Assignments) report. | PRB2001909 | 2022-07-01
Pay \ RTI \ FPS | Employees are omitted from the NHS RTI FPS where they have been terminated and rehired the following day. | PRB2002145 | 2023-01-01
Pay \ RTI \ FPS | The FPS archive is reflecting period values in the Year-to-Date value fields for payroll benefits in-kind. In cases where those values are negative the FPS will error. | PRB2002246 | 2022-10-01
Pay \ RTI \ FPS | The NHS RTI FPS XML Process is omitting period and year to date NI values where an employee has been terminated and rehired from the following date and is subject to PAYE aggregation. | PRB2002307 | 2022-09-01
Pay \ RTI \ FPS | When the NI Reporting Assignment is transferred to a different Payroll, the RTI FPS archive is excluding the details from the ‘Benefits Taxed Through Payroll NOT Subject to NIC Information’ balance. The RTI FPS archive for the Tax Month does not have the correct details and the RTI YTD Reconciliation Report identifies | PRB2001919 | 2023-03-01
Pay \ RTI \ FPS | Employees who have Zero Payment in the first Pay Period and then has a payment in a Supplementary Run (in the same period), then the NHS RTI FPS does not generate New Starter Details. | PRB2002621 | 2023-10-01
Pay \ RTI \ FPS | The "Period End Date" on the NHS RTI FPS XML Submission page is displaying the incorrect date for Pay Periods in the current Tax year. | PRB2002552 | 2024-01-01
Pay \ RTI \ FPS | The NHS RTI FPS process is omitting the Taxable Pay and Tax Paid values for fully aggregated employees who have been re-hired after the termination date, but before the final process date of the original employment. | PRB2002254 | 2024-02-01
Pay \ RTI \ FPS | The GAYE NHS & GAYE NHS ARRS elements are not feeding through to the "Items Subject To Class 1 NIC" data item on the FPS. | PRB2002744 | 2024-08-01
Pay \ RTI \ Reconciliation | The NHS RTI FPS Amendments XML Process is not including assignments that were Skipped in their last Payroll Run of the tax year. | PRB2001831 | 2022-05-01
Pay \ RTI \ Reconciliation | For employees with multiple assignments, the RTI NI Reporting Assignment is not being switched when the original is ended by the NHS Mass End Assignment (MEA) process. | PRB2002042 | 2022-05-01
Pay \ RTI \ Reconciliation | Where multiple instance of the NHS RTI FPS Amendments is run, only the initial instance can generate the RTI YTD Reconciliation report. | PRB2002062 | 2022-01-01
Pay \ RTI \ Reconciliation | The NHS RTI YTD Reconciliation Report will overstate the Student Loan amount for employees having both Student Loan and Post Graduate Loan. | PRB2002242 | 2022-07-01
Pay \ RTI \ Reconciliation | When the NHS RTI Year to Date Reconciliation Report is run retrospectively for a previous tax year, it incorrectly reports EYU figures which are related to a later tax year. | SR1494282 | 2022-11-01
Pay \ RTI \ Reconciliation | The NHS RTI reconciliation report may not report correct details where an employee has a break in service. | SR1697356 | 2022-05-01
Pay \ RTI \ Reconciliation | Following on from the completion of a Concurrent Requests, when clicking on 'View Details' on the Child Request the following message will be displayed 'Validation Else'. | PRB2002451 | 2023-09-01
Pay \ RTI \ Reconciliation | When an employee has multiple assignments that are aggregated for NI across payroll frequencies, the NHS RTI FPS is not reporting the BIK YTD values where the primary reporting Assignment is not processed in that Run. | PRB2002650 | 2023-11-01
Performance \ BI | The NHS Compliance Dashboard Competency Matching analyses can fail to complete and users experience a timeout error after 30 mins. | PRB2002147 | 2022-02-01
Performance \ BI | The NHS Learning Administration Dashboard- Learning Record (All Delegates) analysis can fail to complete when Enrolment Status filter is selected as Confirmed. | PRB2002183 | 2023-01-01
Performance \ BI | The NHS Staff in Post Dashboard Monthly Staff in Post analyses does not complete when the User selects a combination of Org L7 and Staff Group in the Group By prompt. | PRB2002197 | 2022-05-01
Performance \ BI | The NHS Assignment Changes Dashboard - Workforce Movements analysis can fail to complete when BI accessed via a devolved responsibility. | PRB2002227 | 2022-10-01
Performance \ BI | The NHS National Returns Dashboard Gender Pay Gap analysis can fail to return data for Employing Authorities with large data sets. If users experience this issue, please raise a call. | PRB2002234 | 2022-05-01
Performance \ BI | The NHS Change Event log Dashboard Employee Highlights analyses does not always complete for larger organisations. | PRB2002464 | 2023-06-01
Performance \ Data Warehouse | Assignment Data is incorrectly available to be reported for Cancelled Applicant Hires. | PRB2002060 | 2022-01-01
Performance \ Data Warehouse | Headcount figures within the ESR Data Warehouse may be inaccurate due to the NHS Employee Unique ID Creation Process not picking up all records. | PRB2002296 | 2022-09-01
Performance \ Data Warehouse | Following changes to rename Job Roles in June 2022, any positions created or updated with the affected Job Roles are incorrectly displaying the old name value in the Strategic Data Warehouse. All other positions are displaying the correct information. | PRB2002496 | 2023-07-01
Performance \ ESR | When attempting Organisational Diagrammer the following error message is returned. 'The application was unable to establish a connection with the TCF socketserver running at https://myesr.nh.suk/OA_HTML please contact your system administrator.' | PRB2002276 | 2022-10-01
Performance \ ESR | OAF pages do not close when using the Close Window menu option when using browsers other than Internet Explorer. | PRB2002184 | 2023-03-01
Performance \ ESR | The Batch Element Entry Lines Upload Page and Batch Element Entry Review Page Hints and Tips is displaying Message Code instead of Message Text. | PRB2002349 | 2023-03-01
Performance \ ESR | The email address held against user accounts is being incorrectly updated to ‘$Sys_Def$’ in certain scenarios. The email address on the employee person record is unaffected. | PRB2002477 | 2024-01-01
Performance \ ESR | The Play button within the My e-Learning portlet isn't working on IPAD Devices using Safari Browser. Additionally, the scroll bar is not visible for users on the Learner Homepage to scroll to the Play button. | PRB2002355 | 2024-02-01
Performance \ Learning Management | Users can encounter an unexpected error message ’Error cannot display page’ when using Learning Administration / Manager Self Service. If a User subsequently retries the action this will be successful. | PRB2002231 | 2022-05-01
Portal | Web content that contains email or telephone number hyperlinks cannot be updated or created. | PRB2002627 | 2023-09-01
Portal | The My ESR Calendar portlet incorrectly displays the class start time as the actual start time + 1 hour. | PRB2002644 | 2024-01-01
Portal | The Manage Internet Access button is not displayed to users who have closed it. If this is the case, users who need to update internet access, including the set up or changing of Multi-factor Authentication settings will need to use Manage Internet Access in the in the left side navigation menu. | PRB2002691 | 2024-04-01
Portal | When a User does not meet the required Update/Reset Password criteria, a generic "Alert" is displayed that does not advise the User what is incorrect. | PRB2002780 | 2024-07-01
Portal \ Configuration | When logging on via the Internet, the control menu is incorrectly displayed for users with the following responsibilities: XXX Portal Site Administrator XXX Content Administrator XXX Content Editor | PRB2001431 | 2022-12-01
Portal \ Configuration | Users are unable to close a 'Popup' message on low resolution mobile devices as it is not possible to view the action button. | PRB2002213 | 2022-05-01
Portal \ Configuration | Webpages fail to load for Java Web Start where the Java Version higher than 1.8.0_281. | PRB2002233 | 2022-05-01
Portal \ Configuration | Events in the ESR events calendar are not being displayed in the correct order. | PRB2002391 | 2023-03-01
Portal \ Configuration | When clicking the Notify Learners on the Upcoming Classes Portlet in the Learning Dashboard, the following message is returned: 'You have encountered an unexpected error. Please contact your system administrator for assistance.' | PRB2002525 | 2023-10-01
Portal \ Configuration | When a Portal Site Administrator views the My Applicant Checklist Portlet on the Applicant Dashboard the warning message "Error: common-error-invalid-responsibility" is displayed. | PRB2002605 | 2024-01-01
Portal \ Configuration | Icons in the My Favourites portlet are not displaying correctly. | PRB2002622 | 2024-01-01
Portal \ Configuration | Job Roles renamed as part of NWD 3.4 display the old value as well as the new value in the Staff Group/Job Roles section for Portal Metadata.” | PRB2002566 | 2024-02-01
Portal \ Configuration | When a user has XXX Site Administrator and one of XXX Content Editor or XXX Content Administrator URPs, then the control menu icon is not displayed. | PRB2002692 | 2024-02-01
Portal \ Configuration | When a user has XXX Site Administrator and one of XXX Content Editor or XXX Content Administrator URPs, then the Portal administration menu item is not displayed. | PRB2002693 | 2024-02-01
Portal \ Configuration | Users with manage subscriptions email for Notices receive both new and existing content references within the Emails. This includes content previously received. E.g. Release Notice update includes multiple items with reference to those deployed up to 1 year ago. | PRB2002154 | 2024-04-01
Portal \ Configuration | Portal Site Administrators are unable to create events in the My ESR Calendar portlet and the following message is displayed 'Calendar is temporarily unavailable. | PRB2002642 | 2024-04-01
Portal \ Configuration | Users are unable to upload *.bmp images to web content and announcements. | PRB2002731 | 2024-05-01
Portal \ Configuration | On the ESR Login Page, the subheading 'Log in with your credentials' is displayed in a larger font size than expected. | PRB2002753 | 2024-07-01
Portal \ Configuration | Within the Unsuccessful Login Attempts screen, the 'Unsuccessful login attempts since your last successful logon...' heading is displayed in a larger font size than expected. | PRB2002760 | 2024-08-01
Portal \ Dashboard | Within the 'My Employment Portlet' inactive assignments are incorrectly displayed. | PRB2001447 | 2023-01-01
Portal \ Dashboard | On the 'My Compliance' Portlet the information icon on the 'Play' button can in some cases display out of date information. | PRB2001481 | 2023-01-01
Portal \ Dashboard | The My Applicant dashboard fails to load if a user has a special character in email address. | PRB2001718 | 2022-10-01
Portal \ Dashboard | Portal Site Administrators will encounter the following error if the same email is attached to more than one user account: '..An unexpected error occurred with the publication process....' | PRB2002040 | 2022-05-01
Portal \ Dashboard | The Play Button not always available in the My Compliance Portlet. | PRB2002144 | 2022-05-01
Portal \ Dashboard | When a Manual Update is made to the Player Status via the Update Player Status button on the Enrolments and Subscriptions page or the Enrolments page. If the class the update has been made to is part of a certification, which the learner is subscribed to then the updated player status is not reflected in Self Service | PRB2002165 | 2022-10-01
Portal \ Dashboard | Users will receive the following error when updating the Address details in the My Applicant Details Portlet where the Mobile/Home/Work Number/Email Address fields are not populated 'The request could not be processed, please try again later'. Users should note the changes to the record will still be saved. | PRB2002250 | 2022-10-01
Portal \ Dashboard | Users are unable to make date tracked changes to address details via the Portal. | PRB2002328 | 2023-01-01
Portal \ Dashboard | Portal Site Administrators may see text in portlets displayed in Welsh on the Staging server. This does not impact the text in the portlets when published to live. | PRB2002398 | 2023-02-01
Portal \ Dashboard | Users are unable to view their twitter feed in ESR Portal/ESR Hub. | PRB2002492 | 2023-03-01
Portal \ Dashboard | The Annual Leave entitlement for Welsh Organisations does not include the additional 7.5 hours specific to Wales from 2023/24 onwards. Additionally the Include Bank Holidays = Yes GRR have been incorrectly updated for both NHS and CYM. | PRB2002502 | 2023-03-01
Portal \ Dashboard | The field Last Updated/Verified does not display correctly on tablet devices in the My Personal Information and the My Equality and Diversity portlets. | PRB2002447 | 2023-07-01
Portal \ Dashboard | Within the My Compliance Portlet, users are unable to close the pop up that is displayed when clicking the 'Status Icon'. This affects Users using a mobile device (Iphone). | PRB2002304 | 2023-09-01
Portal \ Dashboard | Within the My Applicant Details and the My Personal Information Portlets, the ‘Immunisations and Checks’ hyperlink is incorrectly displayed to Users who do not have Occupational Health data entered. | PRB2002543 | 2023-09-01
Portal \ Dashboard | The ‘Reassign Notifications to Supervisor’ request will complete with a warning if the user is associated with more than one ESR user account’ | PRB2002454 | 2023-10-01
Portal \ Dashboard | Within the My Bank Account Details Portlet, users are not able to view recent updates to Bank Sort Codes | PRB2002544 | 2024-01-01
Portal \ Dashboard | The Upcoming Classes and Updates Attendance Portlets on Learning Dashboard Portal fail to load where a class has a Venue name of more than 100 characters. | PRB2002553 | 2024-01-01
Portal \ Dashboard | The My Personal Information portlet can fail to load for External Learners and display the following message: 'The Error: An unexpected problem occurred when accessing ESR, please try again later .' | PRB2002597 | 2024-01-01
Portal \ Dashboard | In the Update Attendance portlet, information can be displayed in the wrong column, if an administrator is displaying the organisation column and sorts the data after updating an enrolment. | PRB2002603 | 2024-01-01
Portal \ Dashboard | The NHS RTI FPS 2023/24 process cannot be selected from the Payroll Concurrent Manager Portlet User. | PRB2002611 | 2024-01-01
Portal \ Dashboard | When accessing the XXX External Learner URP via W3 the navigation to My Personal Information (My Personal Information > Personal Information) is not displayed in the left hand navigation menu. | PRB2002612 | 2024-01-01
Portal \ Dashboard | When clicking on the Notify Learners in the Upcoming Classes portlet, the notification text subject line does not include the Class Start Date and Class Location. | PRB2002654 | 2024-01-01
Portal \ Dashboard | The Upgrade Access button is incorrectly displayed to some Users with Employee Self Service and Employee Self Service limited access URPs. | PRB2002689 | 2024-02-01
Portal \ Dashboard | The 'View' button on the 'My Compliance' Portlet is disabled even when the user is already enrolled onto a class that delivers the competency in the future. | PRB2001480 | 2024-04-01
Portal \ Dashboard | Pre-Allocated Exceptions are not being included in the "My" and "Team" count displayed on the Payroll Exceptions portlet. | PRB2002541 | 2024-04-01
Portal \ Dashboard | If the Announcement portlet is removed from the Applicant Dashboard then it cannot be readded. | PRB2002610 | 2024-04-01
Portal \ Dashboard | When the My Compliance Portlet is expanded, the information is not displayed correctly. | PRB2002634 | 2024-04-01
Portal \ Dashboard | Within the Documents and Media Portlet, Users are unable to download document published at Organisational level. However, Users are able to search for the document and download from the Search Details Portlet. | PRB2002715 | 2024-04-01
Portal \ Dashboard | When a user clicks on View Class in the Update Attendance Portlet, the note advising the user that minimum attendance has not been met, does not display for the previous 7 days of classes. | PRB2002607 | 2024-08-01
Portal \ Dashboard | When changing the Sort Order on the View Classes in the Update Attendance Portlet, the link to 'Navigate to Catalogue Search' is not displayed. | PRB2002609 | 2024-08-01
Portal \ Dashboard | In the "My Pay Details" portlet, additional historical assignments are being displayed. | PRB2002793 | 2024-08-01
Portal \ Dashboard | Within the Upcoming Classes portlet of the Learner Dashboard, the 'Notify Learners' button will display an error 'Page Security cannot be asserted…' and not notify learners when the location code for the class is 'NULL'. | PRB2002778 | 2024-08-01
Portal \ Dashboard | Within the My Pay Details Portlet, the "View My Payslip/P60/P11D" buttons are not active for Users with additional terminated Assignments, even when the User has Payslips. | PRB2002797 | 2024-08-01
Portal \ Dashboard | Within the My e-Learning portlet, the 'Play' button is incorrectly enabled for expired Learning certifications. | PRB2002772 | 2024-09-18
Reporting | The folder 'Wfc Conflict of Interests' under 'WorkForce Composition' Subject Area has incomplete and/or inaccurate data. | PRB2002265 | 2022-10-01
Reporting \ BI | Users are presented with an error message when exporting large amounts of data in Excel format. We advise Users where practical to export to csv or tsv format. | PRB2000297 | 2022-10-01
Reporting \ BI | When exporting analyses, the filter criteria (parameters) is not included in the export. | PRB2000374 | 2023-01-01
Reporting \ BI | When exporting data from the NHS Staff in Post Dashboard Detail Tab to excel, the Title, Gender and Age Band fields can display as blank. | PRB2000954 | 2022-12-01
Reporting \ BI | When scheduling reports the following error message can be encountered including 'Job was failed' narrative. | PRB2001162 | 2022-12-01
Reporting \ BI | The 'Notified Termination Date' is including the Timezone within the Workforce Subject Area. | PRB2001435 | 2022-05-01
Reporting \ BI | When Users attempt to save current customisations in the ‘NHS Change Event Log Dashboard, Employee tab a message is returned which begins with the following narrative. 'The current XML is invalid.....' | PRB2001517 | 2022-12-01
Reporting \ BI | Bars charts set to the default format can randomly render in 2D or 3D. | PRB2001553 | 2022-12-01
Reporting \ BI | Competence Requirements at Business Group Level pertaining to Merged Employing Authorities are not being cascaded to all posiitons within the Merged VPD. | PRB2001880 | 2022-12-01
Reporting \ BI | Within the Workforce Profile Subject Area, Organisations are still showing the Department Manager Name even though they are no longer active in the Organisation. | PRB2001960 | 2023-01-01
Reporting \ BI | External Learners may be omitted from some workforce based NHS Standard Dashboards including the NHS Staff in Post Dashboard. | PRB2002046 | 2022-01-01
Reporting \ BI | The NHS IAT Dashboard-Details tab has the 'Initiated by' data overwritten by 'PDS Copied by' data when the PDS is actioned. | PRB2002075 | 2022-01-01
Reporting \ BI | The NHS Staff in Post Dashboard - Monthly Staff in Post analysis will time out on some occasions when filtered by organisations hierarchy level. | PRB2002096 | 2023-01-01
Reporting \ BI | The NHS Staff in Post Dashboard Apprenticeship Summary Analyses, In Progress Apprentices NI Category RAG Status displays the following message “Odbc driver returned an error”. | PRB2002097 | 2022-02-01
Reporting \ BI | E-learning records can have a creation date that is a later than the Date First Played. | PRB2002100 | 2022-01-01
Reporting \ BI | Performance fix for the BI NHS Compliance Dashboard - Selective Competency Matching Analysis and failed to complete when 30 or more competencies are selected. | PRB2002109 | 2022-02-01
Reporting \ BI | The NHS employee relations dashboard – employee relations list analysis is failing to complete with the following error message “ODBC Driver returned an error”. | PRB2002126 | 2022-01-01
Reporting \ BI | Within the Workforce Subject Area, when combining the 'Date From' and 'Date To' columns from the Organisation Folder with columns from the Position Organisation Cost Centre folder causes the analyses to fail with an error. | PRB2002136 | 2022-05-01
Reporting \ BI | Date related data items are being displayed in analyses with a blue header. | PRB2002142 | 2022-03-01
Reporting \ BI | Employee absences are omitted from the NHS Absence Dashboard, Individual Absence Analysis due to incorrect data held against secondary assignments. | PRB2002159 | 2022-02-01
Reporting \ BI | The 'Manager Flag' field located the Assignment Folder should not display a null value. | PRB2002179 | 2022-03-01
Reporting \ BI | The NHS Change Event Log Dashboard - Other Highlights analyses incorrectly reports changes made to the Employee Bank Account when the employee has been terminated. | PRB2002180 | 2023-01-01
Reporting \ BI | In the event of an employee having a reverse termination the associated update to the Pension NHS element is not being reflected. | PRB2002182 | 2022-02-01
Reporting \ BI | When the data item 'Change Value' is selected from the Salary Details folder in the Human Resources - Audit Change Event Subject Area will return and ODBC error. | PRB2002199 | 2022-05-01
Reporting \ BI | An employee's FTE data is not accurately reported where the employee has gap in their FTE data within ESR. This can affect records prior to December 2021. | PRB2002203 | 2022-05-01
Reporting \ BI | The NHS Absence Dashboard Individual Absence analyses is omitting Open Ended Future Dated periods of Maternity and Sickness Leave. | PRB2002205 | 2022-07-01
Reporting \ BI | NHS Staff in Post Dashboard - CRS Detail analysis can fail to complete. | PRB2002221 | 2022-05-01
Reporting \ BI | The NHS Compliance Dashboard - positions without requirements analysis omits newly created positions which have been created without attached competence requirements. | PRB2002226 | 2022-05-01
Reporting \ BI | The FTE value in both the Workforce and Absence Subject Areas may be missing for employees who previously had corrupted person/assignment data. | PRB2002229 | 2022-10-01
Reporting \ BI | The NHS Absence Dashboard - Staff List analysis is timing out and not returning data. | PRB2002230 | 2022-05-01
Reporting \ BI | The 'Actual Salary' data item is returning incorrect values in the Absence and Workforce Profile subject areas for some employees who previously had multiple offscale/salary sacrifice element entries with the same effective dates but then has one or more subsequently deleted. | PRB2002255 | 2023-01-01
Reporting \ BI | 'Human Resources - Absence' subject area is excluding absence records of employees who were included in a MOCP whilst on leave. | PRB2002264 | 2022-09-01
Reporting \ BI | The NHS Staff in Post Dashboard, Detail analyses does not display the 'Location' column for some assignments where the Location is linked with the new GEO related records.. | PRB2002267 | 2022-08-01
Reporting \ BI | Name changes made to employees recorded as a 'Department Manager override' are not being reflected in NHS Staff in Post Dashboard, Detail Analyses | PRB2002272 | 2022-10-01
Reporting \ BI | The NHS Financial Cost Analysis Dashboard may be incomplete for records which have been historically corrected. | PRB2002275 | 2022-07-01
Reporting \ BI | Within the usage Tracking Subject Area including columns 'HOUR' and 'MINUTE' in an analysis will cause that analysis to fail. | PRB2002284 | 2022-08-01
Reporting \ BI | The column ‘Change Count ‘ will be added to the Audit Change Event folder within the "Human Resources - Audit Change Event" subject area. | PRB2002291 | 2022-08-01
Reporting \ BI | The NHS Employee Relations Dashboard - Capability No UHR analyses can fail to complete resulting in a error message being dispalyed. | PRB2002314 | 2022-09-01
Reporting \ BI | The NHS User Administration Dashboard, Details Analyses is showing incorrect 'Latest Start Date' for employees. | PRB2002324 | 2022-10-01
Reporting \ BI | The NHS Position Analysis Dashboard - Detail Analysis is returning previous version of the Subjective Code against some Positions. | PRB2002329 | 2022-10-01
Reporting \ BI | The data item 'Completion Date' within the Appraisal folder is incorrectly reporting the Completion Date of the Learning Path and not the Appraisal. | PRB2002360 | 2022-10-01
Reporting \ BI | The NHS Staff in Post Dashboard, Staff List Analyses does not include records when an employee hire date is changed to an earlier date. | PRB2002369 | 2023-01-01
Reporting \ BI | The Total Duration (Days) field within the Absence Detail analysis does not adjust where the duration days has been manually amended in the absence record (in ESR). | PRB2002384 | 2023-01-01
Reporting \ BI | The NHS Change Event Log Dashboard PAYE and NI Highlights Analysis errors when the users export the results to excel. | PRB2002437 | 2023-01-01
Reporting \ BI | Within the Absence Subject Area, data is not returned when the 'Time.Date' filter = CURRENT_DATE. | PRB2001888 | 2023-02-01
Reporting \ BI | The Downtime Payslip View Events are not visible to Users in ESRBI. | PRB2002368 | 2023-02-01
Reporting \ BI | The NHS User Administration Dashboard Detail analysis excluding records when filtered by Users who have a person type of 'Contact'. | PRB2002412 | 2023-02-01
Reporting \ BI | Payroll records are no longer visible in ESRBI when a Payroll rollback process overlaps with a National ESRBI process which runs between 12:00 and 13:00 every Saturday. | PRB2002418 | 2023-02-01
Reporting \ BI | Appraisal Analyses include the 'Main Reviewer' field can return duplicate rows when the Main Reviewer has a date tracked delete. | PRB2002425 | 2023-02-01
Reporting \ BI | The NHS Learning Administration Dashboard - Selective Course Completions Analyses can fail to complete for larger organisations. | PRB2002365 | 2023-03-01
Reporting \ BI | The NHS Absence Dashboard Annual Leave Balances analysis is incorrectly including annual leave booked after an employee's termination date in the Leave Booked column. | PRB2002379 | 2023-03-01
Reporting \ BI | The NHS Employee Dashboard - Disciplinary Analysis does not complete for larger organisations, when a date range greater than one year is selected in the parameters. | PRB2002436 | 2023-03-01
Reporting \ BI | Within the Human Resources Audit Change Event Subject Area, the "Change Count" does not display the correct data. | PRB2002439 | 2023-03-01
Reporting \ BI | Within the Real Time Subject Area, records with a person type of Applicant.Ex-employee are not included in the Recalled Leavers Report folder. | PRB2002547 | 2023-06-01
Reporting \ BI | The 'Supervisor Employee Number' column is incorrectly showing data when the supervisor has been made an Ex-Employee | PRB2002446 | 2023-08-01
Reporting \ BI | The NHS Pension Dashboard Summary Analysis is failing to complete for large organisations. | PRB2002478 | 2023-08-01
Reporting \ BI | Actual Salary for employees who had Spot Salary or Off Scale element update between 2nd January and 26th January 2023 may be incorrect when reported in ESRBI. | PRB2002571 | 2023-09-01
Reporting \ BI | The NHS Change Event Log Dashboard Employee Highlights analyses does not complete for some of the large organisations. | PRB2002578 | 2023-09-01
Reporting \ BI | The NHS Medical & Dental Dashboard - Deanery Post Detail Analyses and the NHS Projected New Starter Alert may return an error when run. | PRB2002602 | 2023-09-01
Reporting \ BI | When attempting to amend or delete an Agent via Edge Browser in ESRBI user may encounter a 'Sax parser returned an exception...' error. | PRB2002586 | 2023-10-01
Reporting \ BI | Within the Workforce Subject Area, salary information is incorrectly displayed for existing employees who have had an application terminated. | PRB2002589 | 2023-10-01
Reporting \ BI | The NHS Learning Administration Dashboard, Learning Record (All Delegates) analysis can incorrectly return a previous 'Date First Played' value when a subsequent attempt is made by an employee. | PRB2002619 | 2023-10-01
Reporting \ BI | While scheduling BI Publisher reports, the folder listing the reports is not closed after selecting the required report. | PRB2002580 | 2023-12-01
Reporting \ BI | Within the Absence Subject Area, data is not returned when the 'Time.Date' filter = CURRENT_DATE. | PRB2002491 | 2024-01-01
Reporting \ BI | The NHS Staff in Post Dashboard, Conflict of Interest Details analyses does not display employees who had a Conflict of Interest declaration record and then deleted it. | PRB2002554 | 2024-01-01
Reporting \ BI | Terminated employees of type applicant.ex-employee are not currently eligible to be picked up by the ‘NHS Payroll Dashboard.Recalled Leavers’ analysis. | PRB2002564 | 2024-01-01
Reporting \ BI | The Position Competency Requirements analysis within the NHS Compliance Dashboard is returning multiple rows when the competence requirement is inherited from a previous job title, which has since been updated by the recent National Workforce Dataset uplift. | PRB2002635 | 2024-01-01
Reporting \ BI | The NHS Staff in Post Dashboard - Detail analyses return incorrect values in 'Actual Salary' and 'Full Time Salary' columns when the 'Off Scale Difference NHS' has been deleted or updated with a new value. | PRB2002643 | 2024-01-01
Reporting \ BI | Users may encounter performance issues when creating local analyses containing Additional Supervisor fields. | PRB2002658 | 2024-02-01
Reporting \ BI | The BI NHS Data Quality Dashboard - Trending Analysis is wrongly reporting positions as being on the incorrect occupation code. | PRB2002665 | 2024-02-01
Reporting \ BI | Where users analyses contain references to the fields 'Insolvency Check', 'Disqualified Directors Register Check' and 'Self-Declaration Form Signed' previously located within the Employment Checklist Details EIT, the fields will no longer return data. | PRB2002671 | 2024-02-01
Reporting \ BI | All instances of Pay Affecting Pay Step Date will return a null value where the Pay Step date falls on the first of the month. | PRB2002679 | 2024-03-01
Reporting \ BI | When a new assignment is created for an existing supervisor, the Supervisor Indicator flag can be removed which incorrectly excludes employees who are Supervisors. | PRB2002657 | 2024-04-01
Reporting \ BI | Element entries which are deleted in ESR are still displayed in ESRBI and, hence incorrectly included in Dashboards. | PRB2002678 | 2024-04-01
Reporting \ BI | The BI Publisher Job History report does not display until the Zoom function on the browser is clicked. | PRB2002585 | 2024-07-01
Reporting \ BI | The NHS Staff in Post Dashboard, Staff in Post Detail analysis is omitting employees where the associated Supervisor's record has been subject to Date Tracked change. | PRB2002684 | 2024-07-01
Reporting \ BI | Latest Start Date will return a null value where the Employee Person Type is External Learner. | PRB2002711 | 2024-07-01
Reporting \ BI | The ‘Payroll Approval Role’ column, within the Organisation folder, does not return the correct data for some organisations when the Role Name has been updated/renamed. | PRB2002734 | 2024-07-01
Reporting \ BI | When changes are made to the ‘Maximum Waitlist’ value, they are not currently being reflected in ESRBI. Therefore, the value in the field can be inconsistent where the value has been updated in ESR. The data is corrected and is accurate on each Tuesday and Thursday. | PRB2002762 | 2024-07-01
Reporting \ BI | The Change Event Log records in ESR are not reflecting changes to the Maximum Waitlisted values in the Learning Subject Area. | PRB2002767 | 2024-07-01
Reporting \ BI | When exporting an NHS Dashboard, Users may encounter the following message 'There was an error processing your download. Please check with your administrator'. | PRB2002615 | 2024-07-01
Reporting \ BI | The field Leavers Access Days is not visible in the Organisation, Position Organisation and Employee Organisation folders in ESRBI. | PRB2002794 | 2024-08-01
Reporting \ BI | The 'Employee Citizenship and Visa Permit' folder is incorrectly displayed to Users. | PRB2002782 | 2024-09-18
Reporting \ BI | When a User creates a report based on the Human Resources - Archives Subject Area, a 'View Display' error is displayed. | PRB2002798 | 2024-09-18
Reporting \ BI | Within the NHS Absence Dashboard, the Employee Absence report is returning an error message for large organisations. | PRB2002803 | 2024-09-18
Reporting \ BI | The ‘Payroll Approval Role’ column, within the Organisation folder, does not return the correct data for some organisations when the Role Name has been updated/renamed. | PRB2002814 | 2024-09-18
Reporting \ ESR Reports | The NHS DEA Payment Schedule report does not display the Issuing Authority details. | PRB2000615 | 2022-12-01
Reporting \ ESR Reports | The NHS RTI FPS Amendments XML Process 2020/21 will not process an assignment if its last assignment action was 'Skipped'. | PRB2001998 | 2022-05-01
Reporting \ ESR Reports | The NHS User Responsibilities Report can fail to complete and returns a 'snapshot error' | PRB2002306 | 2022-09-01
Reporting \ ESR Reports | The NHS Gross To Net Summary Report is double counting Basic Pay Standard Hours where there has been a mid period change in salary. | PRB2002321 | 2022-11-01
Reporting \ ESR Reports | The 'NHS Pension Changes and Highlights - Payroll Period' report can fail to complete and returns a snap-shot message when extracting the associated data. | PRB2002381 | 2023-01-01
Reporting \ ESR Reports | The NHS LGPS Band Allocation Report is incorrectly displaying the message "Check band - No grade or spot salary defined" for assignments with a Spot Salary. | PRB2002583 | 2023-09-01
Reporting \ ESR Reports | When updating the NI Category from H to A for an Apprentice who is turning 25, the RTI GB Update NI Category completes in status of Warning with the following message "ORA-20001: Invalid NI category. Category H is only applicable for employees under 25 years of age." | PRB2002516 | 2023-10-01
Reporting \ ESR Reports | In certain scenarios the new starter declaration sent flag is being removed from existing assignments and reporting an error on the Pre-Payroll Exception report. | PRB2002666 | 2023-11-01
Reporting \ ESR Reports | The NHS Third Party Element Listing Report omits Retropay run results if no Deduction Type is returned within the Arrears Element. | PRB2002471 | 2024-02-01
Reporting \ ESR Reports | The NHS Periodic Pension List Report returns the original employee address regardless of the report effective date when an employee has multiple addresses. | PRB2002695 | 2024-04-01
Self Service | Personal Information and Contacts continues to display the Review and Confirmation pages. | PRB2000538 | 2023-02-01
Self Service \ Admin | When an administrator submits an action for an employee with an additional supervisor, then the approval is sent to the employee's additional supervisor instead of being directed to the administrator's manager. | PRB2001336 | 2023-01-01
Self Service \ Admin | Employee records can be terminated even where there is an Open Ended Absence. | PRB2001128 | 2023-02-01
Self Service \ Admin | Users are unable to Hire Applicants over 75 years of Age in SSHR and the following message is displayed: 'Error: ORA-20001 Employee's age must be between 16 and 75, please re-enter birth date.' | PRB2002463 | 2023-02-01
Self Service \ Admin | When attempting to open an attachment within a termination notification, the user is presented with an error message: You have encountered an unexpected error. Please contact your System Administrator for assistance. | PRB2002282 | 2023-03-01
Self Service \ e-Learning | E-learning courses are failing to update course progression for multiple modules and if the course is launched in new window | PRB2002342 | 2023-01-01
Self Service \ e-Learning | After submitting an External Learning request and returning to the Learner Homepage, the following error message is returned: "Error thrown : Unable to determine STC statusORA-06553: PLS-306: wrong number or types of arguments in call to 'IS_STC_LEARNER'"d. | PRB2002687 | 2024-04-01
Self Service \ Employee | When amending Bank details, changes are submitted successfully though the following message is spuriously displayed under amount type: 'You will be paid by cheque until you specify how you wish to be paid.' | PRB2000594 | 2022-02-01
Self Service \ Employee | When clicking the 'Update Action' on an Appraisal Notification the following error message is returned: 'You have insufficient privileges for the current operation. Please contact your System Administrator.' | PRB2001217 | 2023-01-01
Self Service \ Employee | When Absence Start Date is changed to a date outside of the payroll period in which it was initially created, as incorrect error message is returned. | PRB2001726 | 2022-01-01
Self Service \ Employee | Address changes made in the My Personal Information Portlet are saved as a Correction instead of an Update. | PRB2001980 | 2022-05-01
Self Service \ Employee | When there is more than one Payment Method attached to a Payroll, then an incorrect Payment Method can be displayed in Employee Self Service. This can occur when bank details are entered via the My Bank Account Details Portlet | PRB2002061 | 2022-01-01
Self Service \ Employee | The MyESR Dashboard can display an incorrect Assignment Start Date as this is using the Applicant Start Date instead of the Employee Start Date. | PRB2002128 | 2022-02-01
Self Service \ Employee | Users are unable to update their contact details via My Personal Information Portlet where contact details already exist. | PRB2002140 | 2022-05-01
Self Service \ Employee | When clicking 'Update My Contact Details' icon within the 'My Personal Information' portlet the screen is not completely visible for desktops with screen resolutions less than 1400. | PRB2002186 | 2022-02-01
Self Service \ Employee | An employee with no applicant records and 2 assignments with an identical start date can display the incorrect assignment number on the Conflict of Interest Declarations. | PRB2002195 | 2022-05-01
Self Service \ Employee | Local HRMS Systems and User Administration can encounter the following error when attempting to reset a user's password: FRM40735: WHEN-VALIDATE-ITEM trigger raised unhandled exception ORA-29261 | PRB2002225 | 2023-01-01
Self Service \ Employee | The My Applicant Details Portlet and My Equality and Diversity portlets display an error message and an applicant is unable to view or update their details where they have multiple NHS Employment Checklist Detail records. | PRB2002238 | 2022-05-01
Self Service \ Employee | Within the My Talent Profile there is not consistent spacing between the 'More' and 'Show' links on the Performance Objective Option. | PRB2001621 | 2023-02-01
Self Service \ Employee | When a Disability Record is updated as at a Future Date, the new date is not reflected the Disability Info View. | PRB2001759 | 2023-02-01
Self Service \ Employee | Self Service Absence Approvals may not be correctly recorded when multiple absences for a single employee are approved by Supervisors via email. The Notification ID displays as Closed. | PRB2002465 | 2023-03-01
Self Service \ Employee | OLM meeting invites are omitting the following text: 'Please note, declining this meeting request does not cancel your enrolment on the class.' | PRB2002507 | 2023-05-01
Self Service \ Employee | The Competence Expiry and Competence Requirements Change emails repeat the text 'For Your Information' in the subject title | PRB2002505 | 2023-09-01
Self Service \ Employee | The Registrations and Memberships section is not displayed on the NHS Talent Profile Report when run in Printable Profile mode. | PRB2001473 | 2023-09-01
Self Service \ Employee | Employees are unable to make changes to Emergency contacts within the My Personal Information portlet where the relationship field is populated with the value 'Emergency'. | PRB2002503 | 2023-09-01
Self Service \ Employee | When the work phone number is populated for the Emergency Contact in the My Emergency Contact Portlet, any update submitted for a contact number is not registered despite receiving a 'request successful' message. | PRB2002677 | 2024-02-01
Self Service \ Employee | When a User has multiple URPs, the 'Back' button incorrectly returns the User to the navigator page instead of the Portal Dashboard. | PRB2002768 | 2024-08-01
Self Service \ Employee | When an employee is terminated and then re-hired in a subsequent tax year, they cannot view their P60 for the year that the original termination date falls in. The following error is displayed, "Error: Temporary error connecting to backend system". | PRB2002809 | 2024-09-18
Self Service \ Manager | When an Advanced Search is saved within the Organisation Chart it will not be viewable once navigated away from the page | PRB2000393 | 2022-11-01
Self Service \ Manager | When a user has been granted proxy access by more than 10 Managers or Supervisors, the Switch User page does not display all users available for selection. | PRB2000642 | 2022-12-01
Self Service \ Manager | When a Manager performs a Return To Work interview an error message is returned if amendments have been made to the assignment during the period of absence. | PRB2002044 | 2022-01-01
Self Service \ Manager | When replacing an active primary assignment with a Internal Secondment assignment the status is not updated to reflect the change. | PRB2002056 | 2022-12-01
Self Service \ Manager | Duplicate workflow comments are occurring when a comment is made on an SSHR FYA approval notification and the user immediately approves further notifications. | PRB2002249 | 2022-11-01
Self Service \ Manager | When updating the Position and Supervisor for an Assignment, using the Assignment function, the following error can be produced when the change is submitted: 'The HR object is invalid Cause...' This only impacts the XXX Manager Self Service (Payroll Approvals Not Required) responsibility' | PRB2000575 | 2023-02-01
Self Service \ Manager | "When a manager reviews annual leave request email notification the following issue occur:: 1) The following text occurs in place of the 'Subject' [/OA_HTML/OA.jsp?page=/oracle/apps/fnd/wf/worklist/webui/NotifMailerPG&WFRegion=NtfDetail&NtfId=697035565&dbc=DTST&OARF=email&language_code=US&_ti=2120131445&oapc=2&oas | PRB2001375 | 2023-02-01
Self Service \ Manager | Superfluous Horizontal Scroll Bars are displayed in the 'Supplementary Roles People in Hierarchy' form. | PRB2002058 | 2023-03-01
Self Service \ Manager | When an employee's allocated Supervisor is a non-primary assignment, then Flexible Working Requests on the Maintain Flexible Working form do not complete returning the following message: 'You have encountered an unexpected error.' | PRB2002493 | 2023-06-01
Self Service \ Manager | Within the My Team Career Information, the suitability matching graphs for all available options are not loading correctly. | PRB2002357 | 2023-07-01
Self Service \ Manager | OSP entitlements are incorrectly recalculated if any fields on an Absence Record are updated via Self Service. | PRB2002683 | 2024-04-01
Self Service \ Manager | ‘Administrator and Manager Self-Service (Payroll Approvals Not Required) users, receive an 'Invalid workflow setup' error when attempting to terminate non-primary assignments’. | PRB2002718 | 2024-04-01
Self Service \ Manager | When a User has accessed the Org Chart page, they are unable to resume their session following a timeout. | PRB2002620 | 2024-05-01
Self Service \ Manager | When you terminate an employee within Manager Self-Service (MSS) and populate the comments field, and then reverse the termination via HR Forms, the original comments still remain visible in MSS. | PRB2002743 | 2024-06-01
Self Service \ Performance Management Plans | Appraisal records within Supervisor Self Service displays the employee's supervisor as at the start date of the review period when there has been a subsequent change to the Supervisor. | PRB2001411 | 2022-12-01
Self Service \ Supervisor | When the user has both Portal Site Administrator and Content Editor responsibilities then they are unable to publish analyses on the BI Portlet. | PRB2001893 | 2022-12-01
Self Service \ Supervisor | Users are currently unable to create iCalendar entries when clicking on the 'iCalendar' link within notifications. | PRB2002320 | 2023-01-01
Self Service \ Supervisor | The 'e-KSF website' button is being incorrectly displayed in the Competencies section of appraisals. | PRB2002394 | 2022-11-01
Self Service \ Supervisor | The Pay Progression Appraisal 'Reason' List of Values is incorrectly displaying additional values related to the SAS Pay Progression Appraisal. This occurs only in Self Service. | PRB2002577 | 2024-01-01
TRS \ Website | Users are unable to submit a query to Business Services Authority from the TRS website and will receive the following error message: "An unexpected error has occurred. Unable to process Query, please try again later." | PRB2002716 | 2024-04-01